## Projects
Project ID | Project Name | Status | Start Date | End Date | Budget | Actual Cost | Manager
P001 | Website Redesign | In Progress | 2025-01-10 | 2025-04-30 | 120000 | 95000 | Alice
P002 | Mobile App | Completed | 2024-11-01 | 2025-01-20 | 85000 | 82000 | Bob
P003 | Data Migration | Pending | 2025-03-01 | 2025-06-30 | 200000 | 30000 | Carol
P004 | API Integration | In Progress | 2025-02-15 | 2025-05-15 | 60000 | 40000 | Alice
P005 | Security Audit | Completed | 2024-12-01 | 2025-01-10 | 45000 | 45000 | Dave

## Tasks
Task ID | Project ID | Task Name | Assignee | Priority | Progress (%) | Due Date
T001 | P001 | UI Design | Alice | High | 80 | 2025-03-31
T002 | P001 | Backend Dev | Bob | High | 60 | 2025-04-15
T003 | P002 | iOS Build | Carol | Medium | 100 | 2025-01-10
T004 | P002 | Android Build | Dave | Medium | 100 | 2025-01-20
T005 | P003 | Schema Design | Eve | Low | 15 | 2025-04-30
T006 | P004 | Auth Module | Alice | High | 70 | 2025-03-15
T007 | P004 | Payment Module | Bob | High | 50 | 2025-04-30
T008 | P005 | Vulnerability Scan | Dave | Medium | 100 | 2024-12-31

## Members
Member ID | Name | Role | Department | Email | Active
M001 | Alice | Project Manager | PMO | alice@example.com | TRUE
M002 | Bob | Developer | Engineering | bob@example.com | TRUE
M003 | Carol | Developer | Engineering | carol@example.com | FALSE
M004 | Dave | Security Engineer | Security | dave@example.com | TRUE
M005 | Eve | Data Engineer | Data | eve@example.com | TRUE